## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 169
Days In Sprint:
Burndown Chart
User Stories |  | Days (Points Completed) Remaining Effort
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | Task Balance | Percentage Completed
Users see available courses offered by University of Toronto | 19 | 7 | 0 | 3 | 3 | 2 | 4 | 0 | 100%
Users see news of different events and courses | 22 | 8 | 1 | 4 | 1 | 4 | 4 | 0 | 100%
Users ask query if any kind of information needed | 23 | 8 | 1 | 6 | 1 | 2 | 5 | 0 | 100%
Users are able to know about university of Toronto from about page | 23 | 8 | 1 | 6 | 1 | 2 | 5 | 0 | 100%
Users see success stories of previous students | 21 | 6 | 4 | 3 | 2 | 1 | 5 | 0 | 100%
Users see admission information and fees from the website | 15 | 5 | 3 | 2 | 0 | 1 | 4 | 0 | 100%
Users know student research | 17 | 6 | 2 | 3 | 1 | 1 | 4 | 0 | 100%
Users can get online admissions through the website. | 15 | 5 | 3 | 0 | 1 | 3 | 3 | 0 | 100%
Users can find location and contact information from the website. | 14 | 3 | 2 | 2 | 3 | 2 | 2 | 1 | 92.86%
Effort Remaining | 169 | 113 | 96 | 67 | 54 | 36 | 0 | 1 | 99.41%
Ideal Trend | 169 | 160.55 | 152.1 | 143.65 | 135.2 | 126.75 | 118.3
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days